## WAP
Planning Number | PXXX00000065388 | Assigned To | SPHR00551A [PT. RIFANSI DWI PUTRA - RDWD] SMO
Work Area | NORTH/Non Remote
WAP (WORK ASSIGNMENT PROPOSAL) |  |  |  | WAP No: | WDP250000000488
|  |  |  | SPK No: | CCMSPHR/SPK/3700192639
Work Title: |  |  |  | Issued Date:
HO Infill Road and Location Package 376 Well 3T-13E |  |  |  | 2025-06-04
Operation Unit: | Work Location: |  |  |  | Permitting Type:
Project & Technical Engineering | Duri Field |  |  |  | NON GAKKUM
Originator: | Team Name:
Syafruddin | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
RHT2/404/2250311RL/ICC14
Company Representative:
Syafruddin
Work Detail Description: |  |  |  | Attachment(s):
General - Mobilization and Demobilization - Perform materials inventory and project close out report - Develop as built drawing - Inventory and Final Report Services RL Construction - Stake out area for construction - Clearing and grubbing of Road and Location - Supply & install Geotextile (if required) - Hauling of soil material, filling and compacting - Piling foundation for Rig Sub Structure (RSS) and guy - Fabricate & install RSS and Cellar Box - Dismantle RSS & Cellar Box - Installation of property boundary markers - Construction and closing Mud Pit - Road and well pad dress up after rig move out
Proposed Payment Method:
Work Unit Rate
Work Scope: | Work Scope Discipline:
Planed
Start date is related to: |  |  |  |  | End date is related to:
Site KOM |  |  |  |  | MAC
Start Date: | End Date: |  |  | Duration (Day(s)):
2025-06-11 | 2026-01-30 |  |  | 234
Commitment Date (as reference for penalty calculation):
Start : 11-JUN-2025 | End : 30-JAN-2026 |  |  |  | Duration : 234
Actual Date : |  |  |  | PO/SPK Closure Date :
Start : | End : N/A |  |  | Commitment : N/A | Actual : N/A
There's no penalty
Work Type: | Construction Cost (IDR): |  |  |  | Estimate Cost at Completion (IDR):
Work Unit Rate (WUR) | Estimated | : | 1,014,134,700.00 |  | 0.00
Completed? NO
CDN:
Contractor Supervision:
JASA PENGAWASAN KONSTRUKSI UTARA - TPEC

## BOQ
Description |  |  | Unit | Unit Rate |  | Quantity |  | Total Price
|  |  |  | Non Remote | Remote | Non Remote | Remote
PILING | [7 empty] | 0.00
| Install Steel Pipe Pile scope of work | [6 empty] | 86,637,600.00
|  | Install Steel Pipe Pile 8" | Meter | 401,100.00 |  | 216 |  | 86,637,600.00
EARTHWORK & CIVIL | [7 empty] | 0.00
| Earthworks scope of work | [6 empty] | 819,140,000.00
|  | Earthworks Fill from Company Designated Location, Haul & Compacted (with hauling distance from 0.5 KM to 15 KM) | Cu. Meter | 114,800.00 |  | 4400 |  | 505,120,000.00
|  | Earthworks Fill, Haul & Compacted, Additional Cost for Contractor Provided Fill | Cu. Meter | 32,000.00 |  | 4400 |  | 140,800,000.00
|  | Mud Pit Excavation/Construction | Cu. Meter | 40,700.00 |  | 600 |  | 24,420,000.00
|  | Mud Pit Closing, Exclude Additional Dirt Fill | Cu. Meter | 31,000.00 |  | 600 |  | 18,600,000.00
|  | Dress-up Road & Well Pad | Sq. Meter | 3,400.00 |  | 1600 |  | 5,440,000.00
|  | Soil/Dirt Hauling, distance 10-15 km (without compaction) | Cu. Meter | 91,300.00 |  | 1200 |  | 109,560,000.00
|  | Land Clearing and Grubbing | Sq. Meter | 9,500.00 |  | 1600 |  | 15,200,000.00
| Structural Steel Works scope of work | [6 empty] | 32,471,300.00
|  | Install Steel Pipe Culvert size >= 24" diameter | Meter | 1,149,500.00 |  | 15 |  | 17,242,500.00
|  | Install Steel/Wooden Cellar Box | Each | 10,743,800.00 |  | 1 |  | 10,743,800.00
|  | Dismantle Steel/Wooden Cellar Box | Each | 4,485,000.00 |  | 1 |  | 4,485,000.00
| Miscellaneous Works scope of work | [6 empty] | 67,512,400.00
|  | Install Conductor Pipe 24" | Meter | 1,800,000.00 |  | 10 |  | 18,000,000.00
|  | Install HDPE Geomembrane | Sq. Meter | 48,000.00 |  | 600 |  | 28,800,000.00
|  | Dismantle Rig Substructure Foundation | Each | 5,818,900.00 |  | 1 |  | 5,818,900.00
|  | Fabricate and Install Rig Substructure Foundation | Each | 14,893,500.00 |  | 1 |  | 14,893,500.00
SURVEY | [7 empty] | 0.00
| Survey Work scope of work | [6 empty] | 8,109,400.00
|  | Survey Works - Survey & Construction Drawing for Well Program | Package | 8,109,400.00 |  | 1 |  | 8,109,400.00
SOIL & CIVIL TESTING | [7 empty] | 0.00
| Laboratory Testing scope of work | [6 empty] | 264,000.00
|  | Moisture-Density Relations (Compaction) Test, ASTM D1557 | Test | 264,000.00 |  | 1 |  | 264,000.00
TOTAL | [7 empty] | 1,014,134,700.00