## WAP
Planning Number | PXXX00000065403 | Assigned To | SPHR00761A [PT. RIFANSI DWI PUTRA - RDPE] SMO
articleWork Area | SOUTH/Non Remote
articleWAP (WORK ASSIGNMENT PROPOSAL) |  |  |  | WAP No: | 685250000000478
|  |  |  | SPK No: | CCMSPHR/SPK/3700192035
Work Title: |  |  |  | Issued Date:
Road and Location New Well P_MINA25_0029 (Exist. Well 6C-17) |  |  |  | 2025-05-28
Operation Unit: | Work Location: |  |  |  | Permitting Type:
Project & Technical Engineering | Minas Field |  |  |  | NON GAKKUM
Originator: | Team Name:
Deden Kurniawan Putra | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
SSM2/404/3230533DR/ICC14
Company Representative:
Syawal
Work Detail Description: |  |  |  | Attachment(s):
Road and Location Construction work package are: General - Mobilization and Demobilization - Perform materials inventory and project close out report - Develop as built drawing - Inventory and Final Report Services Road & Location - Stake out area for construction - Clearing and grubbing of Road and Location - Hauling of soil material, filling and compacting - Cellar Box and RSS Fabrication - Pilling foundation for RSS, pipe support, Structure and guy line - Cellar Box Installation and Demolition - RSS Installation and Demolition - Installation of property boundary markers - Construction and closing Mud Pit - Road and well pad dress up after rig move out.
Proposed Payment Method:
Work Unit Rate
Work Scope: | Work Scope Discipline:
Planed | Well Programs
articleStart date is related to: |  |  |  |  | articleEnd date is related to:
Site KOM |  |  |  |  | MAC
article Start Date: | End Date: |  |  | Duration (Day(s)):
2025-06-10 | 2025-12-10 |  |  | 184
Commitment Date (as reference for penalty calculation):
Start : N/A | End : N/A |  |  |  | Duration : N/A
Actual Date : |  |  |  | PO/SPK Closure Date :
Start : | End : N/A |  |  | Commitment : N/A | Actual : N/A
There's no penalty
Work Type: | Construction Cost (): |  |  |  | Estimate Cost at Completion ():
Work Unit Rate (WUR) | Estimated | : | 2072114860
Contractor Supervision:
JASA PENGAWASAN KONSTRUKSI SELATAN-PROSYS

## BOQ.
Description |  |  | Unit | Non Remote |  | Remote |  | Total Price
|  |  |  | Rate | Qty | Rate | Qty
PILING | [7 empty] | 0
| Install Steel Pipe Pile | [6 empty] | 0
|  | Install Steel Pipe Pile 4" | Meter | 144000 | 360 |  |  | 51840000
|  | Install Steel Pipe Pile 8" | Meter | 145000 | 700 |  |  | 101500000
|  | Install Steel Pipe Pile 24" | Meter | 1495000 | 24 |  |  | 35880000
EARTHWORK & CIVIL | [7 empty] | 0
| Earthworks | [6 empty] | 0
|  | Earthworks Fill from Company Designated Location, Haul & Compacted, Balanced Cut/Fill (with hauling distance < 0.5 KM) | Cu. Meter | 45000 | 10000 |  |  | 450000000
|  | Earthworks Fill from Company Designated Location, Haul & Compacted (with hauling distance from 0.5 KM to 15 KM) | Cu. Meter | 110000 | 5000 |  |  | 550000000
|  | Earthworks Cut/Excavation | Cu. Meter | 35000 | 2500 |  |  | 87500000
|  | Land Clearing and Grubbing | Sq. Meter | 8000 | 10000 |  |  | 80000000
|  | Mud Pit Excavation/Construction | Cu. Meter | 34000 | 1500 |  |  | 51000000
|  | Mud Pit Closing, Exclude Additional Dirt Fill | Cu. Meter | 30000 | 1500 |  |  | 45000000
|  | Dress-up Road & Well Pad | Sq. Meter | 7990 | 10000 |  |  | 79900000
|  | Soil/Dirt Hauling, distance 0-10 KM (without compaction) | Cu. Meter | 50000 | 5000 |  |  | 250000000
|  | Soil/Dirt Hauling, distance 10-15 km (without compaction) | Cu. Meter | 60000 | 1000 |  |  | 60000000
| Structural Steel Works | [6 empty] | 0
|  | Fabricate and Install Structural Steel | Kilogram | 22000 | 1000 |  |  | 22000000
|  | Install Steel Cellar Box | Each | 9999960 | 1 |  |  | 9999960
|  | Dismantle Steel Cellar Box | Each | 3999900 | 1 |  |  | 3999900
| Miscellaneous Works | [6 empty] | 0
|  | Install HDPE Geomembrane | Sq. Meter | 50000 | 1500 |  |  | 75000000
|  | Fabricate and Install Rig Substructure Foundation | Each | 12500000 | 1 |  |  | 12500000
|  | Dismantle Rig Substructure Foundation | Each | 5000000 | 1 |  |  | 5000000
| Removal/Demolish Works | [6 empty] | 0
|  | Removal/Demolish Steel Structure | Kilogram | 10000 | 500 |  |  | 5000000
|  | Removal/Demolish Reinforced concrete | Cu. Meter | 1000000 | 50 |  |  | 50000000
SURVEY | [7 empty] | 0
| Survey Work | [6 empty] | 0
|  | Survey Works - Survey & Construction Drawing for Well Program | Package | 6000000 | 1 |  |  | 6000000
SOIL & CIVIL TESTING | [7 empty] | 0
| Laboratory Testing | [6 empty] | 0
|  | Moisture-Density Relations (Compaction) Test, ASTM D1557 | Test | 16999000 | 1 |  |  | 16999000
| Laboratory Testing for Soil Properties | [6 empty] | 0
|  | Natural Moisture Content, ASTM D2216 | Test | 4999000 | 1 |  |  | 4999000
|  | Specific Gravity, ASTM D854 | Test | 1000000 | 1 |  |  | 1000000
|  | Bulk Density Test, ASTM D7263 | Test | 6999000 | 1 |  |  | 6999000
|  | Sieve Analysis of Fine and Coarse Aggregates, ASTM C136 | Test | 1000000 | 1 |  |  | 1000000
|  | Atterberg Limit Test, ASTM D4318 | Test | 3999000 | 1 |  |  | 3999000
|  | Particle-Size Analysis for Cohessive Soils ASTM D422 | Test | 4999000 | 1 |  |  | 4999000
TOTAL | [7 empty] | 2072114860

## Sheet1
NO | Description Of work | Area | Team | DRMI | DRMO | Plan Start | Plan finish | SCHEDULE | [29 empty] | KETERANGAN
[8 empty] | JUNI 25 |  |  |  | 2025-07-25 |  |  |  | AGUSTUS 25 |  |  |  |  | 2025-09-25 |  |  |  | OKTOBER 25 |  |  |  | 2025-11-25 |  |  |  |  | DESEMBER 25
[8 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
1 | P_MINA25_0029 | Minas | RDPE | 2025-08-12 | 2025-08-30 | 2025-06-05 | 2025-07-02
| Construction |  |  |  |  | 2025-06-05 | 2025-07-02 | bar: JUNI 25 W2 to 2025-07-25 W1
| RFD |  |  |  |  | 2025-07-02 | 2025-07-02 | bar: 2025-07-25 W1
Clearing & Grubing
Soil Filling & Compacting Until RFD
RFD
After DRMO
Formulas:
Plan Start = [Plan finish, row above]
Plan finish = [Plan finish, row above]