## WAP
Planning Number | PXXX00000061043 | Assigned To | SPHR00761A [PT. RIFANSI DWI PUTRA - RDPE] SMO
Work Area | NORTH/Non Remote
WAP (WORK ASSIGNMENT PROPOSAL) |  |  |  | WAP No: | WDP250000000044
|  |  |  | SPK No: | CCMSPHR/SPK/3700181670
Work Title: |  |  |  | Issued Date:
2025-01-22
Operation Unit: | Work Location: |  |  |  | Permitting Type:
Project & Technical Engineering | Duri Field |  |  |  | NON GAKKUM
Originator: | Team Name:
Syafruddin | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
tba
Company Representative:
Andreas Siregar
Work Detail Description: |  |  |  | Attachment(s):
Contractor to construct HO Road and Location Package 294 Well 9N-18A |  |  |  | - WPR WDP250000000044 COD 20250410.pdf
- RFI 1st SPK CCMSPHRSPKWDP250000000044 HO Road and Location Package 294 Well 9N-18A.pdf
- Attendance List dan MoM SiteKOM 9N-18A.pdf
- WPR SPK WDP250000000044 HO Road and Location Package 294 Well 9N-18A - 20250228.pdf
- MB02_RLHO_P294_9N18A_RDP.xlsx
- Lampiran Excavation Mud Pit_RLHO_P294_9N18A_RDP.pdf
- WPR WAP WDP250000000044 COD 27022025.pdf
- JS02_RLHO_P294_9N18A_RDP.pdf
- Lampiran Distribusi Hauling_RLHO_P294_9N18A_RDP.pdf
- Lampiran Install Geomembrane_RLHO_P294_9N18A_RDP.pdf
- Lampiran Land Clearing and Grubbing_RLHO_P294_9N18A_RDP.pdf
- Lampiran Distribusi Hauling_RLHO_P294_9N18A_RDP.pdf
- Lampiran Supply Install Geotextile_RLHO_P294_9N18A_RDP.pdf
- MB01_RLHO_P294_9N18A_RDP.xlsx
- Lampiran Estimasi Volume Penimbunan_RLHO_P294_9N18A_RDP.pdf
- JS01_RLHO_P294_9N18A_RDP.pdf
- MB03_RLHO_P294_9N18A_RDP.xlsx
- JS04_RLHO_P294_9N18A_RDP.pdf
- Lampiran Pilling 04_RLHO_P294_9N18A_RDP.pdf
- MB04_RLHO_P294_9N18A_RDP.xlsx
- Lampiran Install RSS
- WPR SPK WDP250000000044 HO Road and Location Package 294 Well 9N-18A - 20250307.pdf
- JS03_RLHO_P294_9N18A_RDP.pdf
- Lampiran Distribusi Hauling_RLHO_P294_9N18A_RDP.pdf
- WPR WAP WDP250000000044 COD 06032025.pdf
- Topo Estimasi 9N-18A.pdf
- Attendance List
Proposed Payment Method:
Work Unit Rate
Work Scope: | Work Scope Discipline:
Planed
Start date is related to: |  |  |  |  | End date is related to:
Site KOM |  |  |  |  | MAC
Start Date: | End Date: |  |  | Duration (Day(s)):
2025-01-30 | 2025-07-31 |  |  | 183
Commitment Date (as reference for penalty calculation):
Start : 30-JAN-2025 | End : 31-JUL-2025 |  |  |  | Duration : 183
Actual Date : |  |  |  | PO/SPK Closure Date :
Start : 30-JAN-2025 | End : N/A |  |  | Commitment : N/A | Actual : N/A
There's no penalty
Work Type: | Construction Cost (IDR): |  |  |  | Estimate Cost at Completion (IDR):
Work Unit Rate (WUR) | Estimated | : | 8746260210 |  | 0
Completed? NO
CDN:
Contractor Supervision:
JASA PENGAWASAN KONSTRUKSI UTARA-TRIPATRA
Work Assignment Result (Original)
Assignment By Plan | Assignment By Process | Construction Cost | Issued Date | Approval Document
RDPE |  | 5057171860 | 2025-01-24 11:14

## BOQ
Planning Number | PXXX00000061043 | Assigned To | SPHR00761A [PT. RIFANSI DWI PUTRA - RDPE] SMO
Work Area | NORTH/Non Remote
WAP (WORK ASSIGNMENT PROPOSAL) |  | WAP No: | WDP250000000044
|  | SPK No: | CCMSPHR/SPK/3700181670
Work Title: |  | Issued Date:
HO Road and Location Package 294 Well 9N-18A |  | 2025-01-22
Operation Unit: | Work Location: |  | Permitting Type:
Project & Technical Engineering | Duri Field |  | NON GAKKUM
Originator: | Team Name:
Syafruddin | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
tba
Work Detail Description:
Contractor to construct HO Road and Location Package 294 Well 9N-18A
Start Date: | End Date: | Duration (Day(s)):
2025-01-30 | 2025-07-31 | 183
Last Bill of Quantity
Description |  |  | Unit | Unit Rate |  | Quantity |  | Total Price | Item Code
|  |  |  | Non Remote | Remote | Non Remote | Remote
PILING | [7 empty] | 0 | 22500
| Install Steel Pipe Pile scope of work | [6 empty] | 80200000 | 22501
|  | Install Steel Pipe Pile 8" | Meter | 145000 | 188500 | 450 |  | 65250000 | 22504
|  | Install Steel Pipe Pile 24" | Meter | 1495000 | 1943500 | 10 |  | 14950000 | 22509
EARTHWORK & CIVIL | [7 empty] | 0 | 22525
| Earthworks scope of work | [6 empty] | 7141967850 | 22526
|  | Earthworks Fill from Company Designated Location, Haul & Compacted (with hauling distance from 0.5 KM to 15 KM) | Cu. Meter | 110000 | 143000 | 26277.1 |  | 2890481000 | 22528
|  | Earthworks Fill from Company Designated Location, Haul & Compacted, Additional Cost per KM Above 15 KM Hauling Distance | Cu. Meter/KM | 5000 | 6500 | 333719.17 |  | 1668595850 | 22529
|  | Additional Cost for Contractor Provided Fill | Cu. Meter | 75000 | 97500 | 26277.1 |  | 1970782500 | 22530
|  | Land Clearing and Grubbing | Sq. Meter | 8000 | 10400 | 18750 |  | 150000000 | 22534
|  | Mud Pit Excavation/Construction | Cu. Meter | 34000 | 44200 | 1300 |  | 44200000 | 22538
|  | Mud Pit Closing, Exclude Additional Dirt Fill | Cu. Meter | 30000 | 39000 | 1300 |  | 39000000 | 22539
|  | Dress-up Road & Well Pad | Sq. Meter | 7990 | 10380 | 7150 |  | 57128500 | 22540
|  | Soil/Dirt Hauling, distance 10-15 km (without compaction) | Cu. Meter | 60000 | 78000 | 5363 |  | 321780000 | 22542
| Canal Works scope of work | [6 empty] | 2992500 | 22556
|  | Construct New Canal width <= 5 M | Cu. Meter | 199500 | 259350 | 15 |  | 2992500 | 22559
| Structural Steel Works scope of work | [6 empty] | 31999860 | 22587
|  | Install Steel Pipe Culvert size >= 24" diameter | Meter | 1200000 | 1560000 | 15 |  | 18000000 | 22598
|  | Install Steel Cellar Box | Each | 9999960 | 12999940 | 1 |  | 9999960 | 22606
|  | Dismantle Steel Cellar Box | Each | 3999900 | 5199870 | 1 |  | 3999900 | 22607
| Miscellaneous Works scope of work | [6 empty] | 1451104000 | 22617
|  | Supply and Install Non-Woven Composite Reinforced Geotextile - Characteristics Short Term Tensile Strength (MD/CD) 40/40 kN/m less then 100/100 kN/m | Sq. Meter | 150000 | 195000 | 9057.36 |  | 1358604000 | 22619
|  | Install HDPE Geomembrane | Sq. Meter | 50000 | 65000 | 1500 |  | 75000000 | 22621
|  | Fabricate and Install Rig Substructure Foundation | Each | 12500000 | 16250000 | 1 |  | 12500000 | 22628
|  | Dismantle Rig Substructure Foundation | Each | 5000000 | 6500000 | 1 |  | 5000000 | 22629
SURVEY | [7 empty] | 0 | 22650
| Survey Work scope of work | [6 empty] | 6000000 | 22651
|  | Survey Works - Survey & Construction Drawing for Well Program | Package | 6000000 | 7800000 | 1 |  | 6000000 | 22654
SOIL & CIVIL TESTING | [7 empty] | 0 | 22656
| Laboratory Testing scope of work | [6 empty] | 16999000 | 22670
|  | Moisture-Density Relations (Compaction) Test, ASTM D1557 | Test | 16999000 | 22098700 | 1 |  | 16999000 | 22672
| Laboratory Testing for Soil Properties scope of work | [6 empty] | 14997000 | 22679
|  | Natural Moisture Content, ASTM D2216 | Test | 4999000 | 6498700 | 1 |  | 4999000 | 22680
|  | Specific Gravity, ASTM D854 | Test | 1000000 | 1300000 | 1 |  | 1000000 | 22681
|  | Atterberg Limit Test, ASTM D4318 | Test | 3999000 | 5198700 | 1 |  | 3999000 | 22684
|  | Particle-Size Analysis for Cohessive Soils ASTM D422 | Test | 4999000 | 6498700 | 1 |  | 4999000 | 22685
TOTAL | [7 empty] | 8746260210