## WAP
Planning Number | PXXX00000051507 | Assigned To | SPHR00551A [PT. RIFANSI DWI PUTRA - RDWD] SMO
Work Area | SOUTH/Non Remote
WAP (WORK ASSIGNMENT PROPOSAL) |  |  |  | WAP No: | WDP240000000516
|  |  |  | SPK No: | CCMSPHR/SPK/3700160301
Work Title: |  |  |  | Issued Date:
Road and Location for new well P_7F-45 |  |  |  | 2024-07-03
Operation Unit: | Work Location: |  |  |  | Permitting Type:
Project & Technical Engineering | Minas Area |  |  |  | NON GAKKUM
Originator: | Team Name:
Deden Kurniawan Putra | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
SSM2/404/3230232DR/ICC14 SSM2/403/3230232DR/TCC03 SSM2/803/3230232FL
Company Representative:
Adetya Hermono
Work Detail Description: |  |  |  | Attachment(s):
Road and Construction work package are: General - Mobilization and Demobilization - Perform materials inventory and project close out report - Develop as built drawing - Inventory and Final Report Services Road & Location - Stake out area for construction - Clearing and grubbing of Road and Location - Hauling of soil material, filling and compacting - Cellar Box and RSS Fabrication - Pilling foundation for RSS, pipe support, Structure and guy line - Cellar Box Installation and Demolition - RSS Installation and Demolition - Installation of property boundary markers - Construction and closing Mud Pit - Road and well pad dress up after rig move out |  |  |  | - WPR WAP WDP240000000516 COD 10032025.pdf
- WPR WAP WDP240000000516 COD 28102024.pdf
- RFI 1st SPK CCMSPHRSPK3700160301 Road and Location for new well P_7F-45 11.pdf
- Lampiran Excavation Canal Part1 _SPK0301_P_7F-45_RDP.pdf
- WPR WAP WDP240000000516 COD 17022025.pdf
- WPR WAP WDP240000000516 COD 24022025.pdf
- WPR WAP WDP240000000516 COD 24042025.pdf
- WPR WAP WDP240000000516 COD 04112024.pdf
- WPR WAP WDP240000000516 COD 03032025.pdf
- WPR WAP WDP240000000516 COD 24032025.pdf
- WPR WAP WDP240000000516 COD 17032025.pdf
- Attandance List.pdf
- WPR WAP WDP240000000516 COD 07042025.pdf
- WPR WAP WDP240000000516 COD 31032025.pdf
- JS01 _SPK0301_P_7F-45_RDP.pdf
- MB01 _SPK0301_P_7F-45_RDP.xlsx
- MB01 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Clearing Grubbing Part3 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Clearing Part1 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Clearing Part2 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Clearing Grubbing Part1 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Clearing Grubbing Part2 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Distribusi Hauling From BP 7E-66 Progress 1.pdf
- Lampiran Excavation Canal Part2 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Install Geotextile Part1 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Install Geotextile Part 2
- Lampiran Geotextile Part 4_02 _SPK0301_P_7F-45_RDP.pdf
- JSR PARTIAL 02 P_7F_45.pdf
- Lampiran Clearing02 _SPK0301_P_7F-45_RDP.pdf
- MB02 _SPK0301_P_7F-45_RDP.pdf
- Lampiran Balance Cut02 _SPK0301_P_7F-45_RDP.pdf
- MB02 _SPK0301_P_7F-45_RDP.xlsx
- Lampiran Distribusi Hauling02 _SPK0301_P_7F-45_RDP.pdf
Proposed Payment Method:
Work Unit Rate
Work Scope: | Work Scope Discipline:
Planed | EARTHWORK & CIVIL
Start date is related to: |  |  |  |  | End date is related to:
Site KOM |  |  |  |  | MAC
Start Date: | End Date: |  |  | Duration (Day(s)):
2024-10-24 | 2025-07-21 |  |  | 271
Commitment Date (as reference for penalty calculation):
Start : 24-OCT-2024 | End : 14-JUL-2025 |  |  |  | Duration : 264
Actual Date : |  |  |  | PO/SPK Closure Date :
Start : 24-OCT-2024 | End : N/A |  |  | Commitment : N/A | Actual : N/A
There's no penalty
Work Type: | Construction Cost (IDR): |  |  |  | Estimate Cost at Completion (IDR):
Work Unit Rate (WUR) | Estimated | : | 8076871599 |  | 0.00
Completed? NO
CDN:
Contractor Supervision:
JASA PENGAWASAN KONSTRUKSI SELATAN-PROSYS
Work Assignment Result (Original)
Assignment By Plan | Assignment By Process | Construction Cost | Issued Date | Approval Document
RDWD |  | 7089833350 | 2024-07-08 15:44

## BOQ
Planning Number | PXXX00000051507 | Assigned To | SPHR00551A [PT. RIFANSI DWI PUTRA - RDWD] SMO
Work Area | SOUTH/Non Remote
WAP (WORK ASSIGNMENT PROPOSAL) |  | WAP No: | WDP240000000516
|  | SPK No: | CCMSPHR/SPK/3700160301
Work Title: |  | Issued Date:
Road and Location for new well P_7F-45 |  | 2024-07-03
Operation Unit: | Work Location: |  | Permitting Type:
Project & Technical Engineering | Minas Area |  | NON GAKKUM
Originator: | Team Name:
Deden Kurniawan Putra | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
SSM2/404/3230232DR/ICC14 SSM2/403/3230232DR/TCC03 SSM2/803/3230232FL
Work Detail Description:
Road and Construction work package are: General - Mobilization and Demobilization - Perform materials inventory and project close out report - Develop as built drawing - Inventory and Final Report Services Road & Location - Stake out area for construction - Clearing and grubbing of Road and Location - Hauling of soil material, filling and compacting - Cellar Box and RSS Fabrication - Pilling foundation for RSS, pipe support, Structure and guy line - Cellar Box Installation and Demolition - RSS Installation and Demolition - Installation of property boundary markers - Construction and closing Mud Pit - Road and well pad dress up after rig move out
Start Date: | End Date: | Duration (Day(s)):
2024-10-24 | 2025-07-21 | 271
Last Bill of Quantity
Description |  |  | Unit | Unit Rate |  | Quantity |  | Total Price | Item Code
|  |  |  | Non Remote | Remote | Non Remote | Remote
PILING | [7 empty] | 0 | 11190
| Install Steel Pipe Pile scope of work | [6 empty] | 210786000 | 11314
|  | Install Steel Pipe Pile 4" | Meter | 294000 | 308700 | 216 |  | 63504000 | 14821
|  | Install Steel Pipe Pile 8" | Meter | 401100 | 421150 | 108 |  | 43318800 | 14823
|  | Install Steel Pipe Pile 12" | Meter | 393800 | 413490 | 264 |  | 103963200 | 14825
EARTHWORK & CIVIL | [7 empty] | 0 | 11194
| Earthworks scope of work | [6 empty] | 5832761359 | 11341
|  | Earthworks Fill from Company Designated Location, Haul & Compacted, Balanced Cut/Fill (with hauling distance < 0.5 KM) | Cu. Meter | 67300 | 70660 | 12000 |  | 807600000 | 15333
|  | Earthworks Fill from Company Designated Location, Haul & Compacted (with hauling distance from 0.5 KM to 15 KM) | Cu. Meter | 114800 | 120540 | 32229.11 |  | 3699901828 | 15334
|  | Earthworks Cut/Excavation | Cu. Meter | 47000 | 49350 | 1000 |  | 47000000 | 15337
|  | Mud Pit Excavation/Construction | Cu. Meter | 40700 | 42730 | 1300 |  | 52910000 | 15341
|  | Mud Pit Closing, Exclude Additional Dirt Fill | Cu. Meter | 31000 | 32550 | 1400 |  | 43400000 | 15342
|  | Dress-up Road & Well Pad | Sq. Meter | 3400 | 3570 | 10704 |  | 36393600 | 15344
|  | Soil/Dirt Hauling, distance 0-10 KM (without compaction) | Cu. Meter | 87900 | 92290 | 5352 |  | 470440800 | 15345
|  | Soil/Dirt Hauling, distance 10-15 km (without compaction) | Cu. Meter | 91300 | 95860 | 2350 |  | 214555000 | 15346
|  | Land Clearing | Sq. Meter | 8100 | 8500 | 17864.86 |  | 144705366 | 17138
|  | Land Clearing and Grubbing | Sq. Meter | 9500 | 9970 | 33247.87 |  | 315854765 | 17139
| Canal Works scope of work | [6 empty] | 73200000 | 11342
|  | Construct New Canal width <= 5 M | Cu. Meter | 73200 | 76860 | 1000 |  | 73200000 | 15354
| Concrete Works for Off Plot scope of work | [6 empty] | 0 | 11343
| Structural Steel Works scope of work | [6 empty] | 70404800 | 11345
|  | Install Steel Pipe Culvert size >= 24" diameter | Meter | 1149500 | 1206970 | 48 |  | 55176000 | 15405
|  | Install Steel/Wooden Cellar Box | Each | 10743800 | 11280990 | 1 |  | 10743800 | 15421
|  | Dismantle Steel/Wooden Cellar Box | Each | 4485000 | 4709250 | 1 |  | 4485000 | 15422
| Miscellaneous Works scope of work | [6 empty] | 1884133540 | 11348
|  | Install Conductor Pipe 24" | Meter | 1800000 | 1890000 | 18 |  | 32400000 | 15455
|  | Install HDPE Geomembrane | Sq. Meter | 48000 | 50400 | 1300 |  | 62400000 | 15457
|  | Dismantle Rig Substructure Foundation | Each | 5818900 | 6109840 | 1 |  | 5818900 | 15465
|  | Install Geo-Textile | Sq. Meter | 99000 | 103950 | 17864.86 |  | 1768621140 | 18587
|  | Fabricate and Install Rig Substructure Foundation | Each | 14893500 | 15638170 | 1 |  | 14893500 | 18588
SURVEY | [7 empty] | 0 | 11197
| Survey Work scope of work | [6 empty] | 0 | 11359
SOIL & CIVIL TESTING | [7 empty] | 0 | 11198
| Laboratory Testing scope of work | [6 empty] | 1105600 | 11361
|  | California Bearing Ratio (CBR) Test, ASTM D1883 | Test | 1105600 | 1160880 | 1 |  | 1105600 | 15718
| Laboratory Testing for Soil Properties scope of work | [6 empty] | 4480300 | 11362
|  | Natural Moisture Content, ASTM D2216 | Test | 1075800 | 1129590 | 1 |  | 1075800 | 15725
|  | Specific Gravity, ASTM D854 | Test | 1136300 | 1193110 | 1 |  | 1136300 | 15727
|  | Bulk Density Test, ASTM D7263 | Test | 1136300 | 1193110 | 1 |  | 1136300 | 15728
|  | Atterberg Limit Test, ASTM D4318 | Test | 1131900 | 1188490 | 1 |  | 1131900 | 16853
TOTAL | [7 empty] | 8076871599