## WAP
Planning Number | PXXX00000066545 | Assigned To | SPHR00761A [PT. RIFANSI DWI PUTRA - RDPE] SMO
articleWork Area | NORTH/Non Remote
articleWAP (WORK ASSIGNMENT PROPOSAL) |  |  |  | WAP No: | WDP250000000614
|  |  |  | SPK No: | CCMSPHR/SPK/3700196841
Work Title: |  |  |  | Issued Date:
Road and location new well P_BEKA25_0003HW |  |  |  | 2025-07-17
Operation Unit: | Work Location: |  |  |  | Permitting Type:
Project & Technical Engineering | Bekasap Area |  |  |  | NON GAKKUM
Originator: | Team Name:
Sori Tua Marganda Lumbantobing | PROJECT WELL DEVELOPMENT
WBS/Cost Center Code:
TBD
Company Representative:
Alexander
Work Detail Description: |  |  |  | Attachment(s):
Construction activity for Well Pad preparation to support Ready For Drilling (RFD) with scope of works as follows: Before DRMI = Stake out area for construction, Clearing & Grubbing, Soil Backfill/Balance Cut, Hauling of Soil fill/Balance cut material, Compaction, Construct mud pit include with installation geomembrane liner, Final Dress up area and Canal Construction/Culvert installation (if needed). After DRMO = Dress up area include with change soil material (if needed) and closing mudpit (include with additional fill)
Proposed Payment Method:
Work Unit Rate
Work Scope: | Work Scope Discipline:
Planed
articleStart date is related to: |  |  |  |  | articleEnd date is related to:
UNKNOWN |  |  |  |  | MAC
article Start Date: | End Date: |  |  | Duration (Day(s)):
2025-08-04 | 2026-02-04 |  |  | 185
Commitment Date (as reference for penalty calculation):
Start : 04-AUG-2025 | End : 04-FEB-2026 |  |  |  | Duration : 185
Actual Date : |  |  |  | PO/SPK Closure Date :
Start : | End : N/A |  |  | Commitment : N/A | Actual : N/A
There's no penalty
Work Type: | Construction Cost (IDR): |  |  |  | Estimate Cost at Completion (IDR):
Work Unit Rate (WUR) | Estimated | : | 2439105260
Contractor Supervision:
JASA PENGAWASAN KONSTRUKSI UTARA - TPEC

## BOQ.
Description |  |  | Unit | Non Remote |  | Remote |  | Total Price
|  |  |  | Rate | Qty | Rate | Qty
PILING | [7 empty] | 0
| Install Steel Pipe Pile | [6 empty] | 0
|  | Install Steel Pipe Pile 4" | Meter | 144000 | 477 |  |  | 68688000
|  | Install Steel Pipe Pile 8" | Meter | 145000 | 36 |  |  | 5220000
|  | Install Steel Pipe Pile 12" | Meter | 280000 | 477 |  |  | 133560000
|  | Install Steel Pipe Pile 24" | Meter | 1495000 | 18 |  |  | 26910000
EARTHWORK & CIVIL | [7 empty] | 0
| Earthworks | [6 empty] | 0
|  | Earthworks Fill from Company Designated Location, Haul & Compacted (with hauling distance from 0.5 KM to 15 KM) | Cu. Meter | 110000 | 8491 |  |  | 934010000
|  | Additional Cost for Contractor Provided Fill | Cu. Meter | 75000 | 8491 |  |  | 636825000
|  | Land Clearing and Grubbing | Sq. Meter | 8000 | 4740 |  |  | 37920000
|  | Mud Pit Excavation/Construction | Cu. Meter | 34000 | 950 |  |  | 32300000
|  | Mud Pit Closing, Exclude Additional Dirt Fill | Cu. Meter | 30000 | 950 |  |  | 28500000
|  | Dress-up Road & Well Pad | Sq. Meter | 7990 | 7600 |  |  | 60724000
|  | Soil/Dirt Hauling, distance 0-10 KM (without compaction) | Cu. Meter | 50000 | 849 |  |  | 42450000
| Structural Steel Works | [6 empty] | 0
|  | Fabricate and Install Structural Steel | Kilogram | 22000 | 12000 |  |  | 264000000
|  | Fabricate Steel Cellar Box | Each | 6999900 | 1 |  |  | 6999900
|  | Install Steel Cellar Box | Each | 9999960 | 1 |  |  | 9999960
|  | Dismantle Steel Cellar Box | Each | 3999900 | 1 |  |  | 3999900
| Miscellaneous Works | [6 empty] | 0
|  | Install HDPE Geomembrane | Sq. Meter | 50000 | 1500 |  |  | 75000000
|  | Dismantle Rig Substructure Foundation | Each | 5000000 | 1 |  |  | 5000000
| Removal/Demolish Works | [6 empty] | 0
|  | Removal/Demolish Unreinforced concrete | Cu. Meter | 1800000 | 10 |  |  | 18000000
SURVEY | [7 empty] | 0
| Survey Work | [6 empty] | 0
|  | Survey Works - Topographic Survey For Inventory | Hectare | 33999000 | 1 |  |  | 33999000
|  | Survey Works - Survey & Construction Drawing for Well Program | Package | 6000000 | 1 |  |  | 6000000
SOIL & CIVIL TESTING | [7 empty] | 0
| Field Testing | [6 empty] | 0
|  | Field Insitu Sand Cone Test, ASTM D1556 | Test | 1799900 | 5 |  |  | 8999500
TOTAL | [7 empty] | 2439105260